## Slide 1
ESSAYS UK · MODEL SAMPLE
Agile Project Kick-off Presentation
NovaFit Booking App Redevelopment
from £15 per 250 words · 350+ UK-qualified writers · essays.uk
Notes: Thank the client board for their time and briefly introduce the team before moving to the agenda slide.

## Slide 2
Agenda
Ten minutes, ten stops: from the problem we are solving through to how we will know the project has succeeded.
Project overview and business case
Aims and objectives
Why agile? The Scrum framework
Scope and deliverables
Team roles and responsibilities
Sprint plan and timeline
Key risks and mitigations
essays.uk · Model presentation sample — for reference and learning only

## Slide 3
Project Overview and Business Case
NovaFit Ltd operates 14 gyms across the North West and currently relies on a booking system built in 2016. Class bookings fail during peak demand, and 22% of app sessions are abandoned before a booking completes (internal…
Member complaints about booking reliability have risen by 30% year on year
A rebuilt app is expected to lift class attendance and reduce call-centre volume by around a quarter
Executive sponsor: Head of Digital, NovaFit Ltd; budget approved for a 12-week build
essays.uk · Model presentation sample — for reference and learning only

## Slide 4
Aims and Objectives
Aim: deliver a reliable, mobile-first booking app within a 12-week programme that restores member confidence in the booking process.
Reduce booking abandonment from 22% to under 8% by the pilot review
Support at least 500 concurrent bookings without failure during peak evening slots
Launch a minimum viable product (MVP) after Sprint 4 for pilot testing at two flagship gyms
Achieve a System Usability Scale (SUS) score above 75 at user testing, benchmarked against the current app score of 52
essays.uk · Model presentation sample — for reference and learning only

## Slide 5
Why Agile? The Scrum Framework
Requirements for the booking flow are expected to change once real members test early releases, which favours an iterative approach over a fixed, sequential plan. A waterfall approach would lock down requirements before any…
Scrum roles: Product Owner (client-facing priorities), Scrum Master (process and blockers), Development Team (build and test)
Two-week sprints, each ending with a working increment demonstrated to the client
Backlog reprioritised after every sprint review based on stakeholder feedback and usage data
A visible burndown chart keeps the team and client aligned on remaining effort
essays.uk · Model presentation sample — for reference and learning only
Notes: If asked why not a traditional waterfall plan, point to the December 2025 pilot where fixed requirements caused three late change requests and a five-week overrun.

## Slide 6
Scope and Deliverables
In scope: class booking, payment integration, push notifications, member profile and a self-service cancellation flow.
MVP deliverable: booking and payment flow, tested on iOS and Android at two pilot sites
Final deliverable: full feature set plus an admin reporting dashboard for gym managers
Handover pack: user documentation and a support runbook for the NovaFit IT team
essays.uk · Model presentation sample — for reference and learning only

## Slide 7
Team Roles and Responsibilities
Product Owner (NovaFit Head of Digital) – owns and prioritises the backlog, and signs off each sprint review
Scrum Master (J. Adeyemi) – facilitates ceremonies, removes blockers and protects the team from scope creep
Development Team (5 students) – front-end, back-end, QA and UX design, self-organising around the sprint backlog
Steering board – reviews progress at each sprint review and approves any change to scope or budget
essays.uk · Model presentation sample — for reference and learning only

## Slide 8
Sprint Plan
Six two-week sprints run across the 12-week programme:
Sprint | Weeks | Focus | Key Deliverable
Sprint 1 | 1–2 | Backlog refinement, environment setup | Product backlog and dev environment live
Sprint 2 | 3–4 | Core booking flow | Class search and booking prototype
Sprint 3 | 5–6 | Payment integration | Working payment gateway (sandbox)
Sprint 4 | 7–8 | Notifications and profile | MVP release for pilot testing
Sprint 5 | 9–10 | Pilot feedback, bug fixes | Stabilised release candidate
Sprint 6 | 11–12 | Admin dashboard, UAT | Final build signed off for launch
essays.uk · Model presentation sample — for reference and learning only
Notes: The Sprint 4 MVP date is the milestone the client cares about most; pause here if the steering board has questions about the pilot cohort.

## Slide 9
Key Risks and Mitigations
Risks are reviewed weekly by the Scrum Master and escalated to the steering board when likelihood or impact increases.
Third-party payment API delay (medium likelihood, high impact) – start sandbox integration in Sprint 1, not Sprint 3
Scope creep from the steering board (medium likelihood, medium impact) – route all change requests through the Product Owner
Team availability during the exam period (high likelihood, medium impact) – front-load complex work into Sprints 2–4
Server load at peak booking times (low likelihood, high impact) – complete load testing before the Sprint 4 pilot
essays.uk · Model presentation sample — for reference and learning only

## Slide 10
Communication Plan
A short, predictable rhythm keeps the client informed without adding administrative overhead to the team.
Daily 15-minute stand-up (team only), covering progress, plans and blockers
Sprint review with the client every two weeks, demonstrating working software rather than slides
Sprint retrospective (team only, immediately after each review) to improve ways of working
Shared backlog and burndown chart updated daily on the project board for full visibility
Ad-hoc escalation channel for blockers that cannot wait for the next stand-up
essays.uk · Model presentation sample — for reference and learning only

## Slide 11
Success Criteria
Success will be judged against measurable targets agreed with the steering board, not general impressions.
Booking abandonment reduced to under 8% at pilot
MVP delivered on schedule at the end of Sprint 4
Zero critical defects outstanding at final sign-off
SUS usability score above 75 from pilot testers
Steering board sign-off achieved at the Sprint 6 review
essays.uk · Model presentation sample — for reference and learning only
Notes: Tie each criterion back to the objectives on slide 4 so the board sees the plan is measurable, not just aspirational.

## Slide 12
Summary and Next Steps
This kick-off has set out why an agile, Scrum-based approach fits a project with evolving requirements, the scope the team is committing to, the roles each person will play, and how progress will be reviewed every two weeks…
Sprint 1 begins Monday, with the first sprint review scheduled in two weeks. The team will circulate the backlog and sprint calendar by email this…
essays.uk · Model presentation sample — for reference and learning only

## Slide 13
References
Schwaber, K. and Sutherland, J. (2020) The Scrum Guide. Scrum.org.
Association for Project Management (2019) APM Body of Knowledge. 7th ed. Princes Risborough: APM.
Highsmith, J. (2009) Agile Project Management: Creating Innovative Products. 2nd ed. Boston: Addison-Wesley.
AXELOS (2018) PRINCE2 Agile. London: TSO.
Brooks, F. P. (1995) The Mythical Man-Month. Anniversary ed. Boston: Addison-Wesley.
essays.uk · Model presentation sample — for reference and learning only